## Mobile App & Web
Sr. No. | Module | Sub-Module | Assumptions/Activities/Screens/Task | GRC Team | Front End | Back End | Testing | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28
1 | BA | Requirement Gathering | Requirement Gathering | Umang | Rishabh | NA | NA | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | Documentation | HR Documentation | Umang | Rishabh | NA | NA |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
|  | Documentation | BD BRD Documentation | Umang | Rishabh | NA | NA | [7 empty] | 1 | 2 | 3 | 4
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
|  | Documentation | PM BRD Documentation | Umang | Rishabh | NA | NA | [11 empty] | 1 | 2 | 3 | 4
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
|  | Documentation | Accounts BRD Documentation | Umang | Rishabh | NA | NA | [15 empty] | 1 | 2 | 3 | 4
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
|  | Documentation | IT BRD Documentation | Umang | Rishabh | NA | NA | [19 empty] | 1 | 2 | 3 | 4
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
|  | Documentation | Quality BRD Documentation | Umang | Rishabh | NA | NA | [23 empty] | 1 | 2 | 3 | 4
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
|  | Documentation | Other Modules BRD Documentation | Umang | Rishabh | NA | NA | [27 empty] | 1 | 2 | 3 | 4
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
2 | Development | Development | Laravel HTML Theme Setup +Role + Database | NA | Nitish/Priyanka | Rajesh/Diksha | Ajay
|  | GRC Management Approval | GRC Management Approval | Umang | NA | NA | NA
3 | HR | Employee Master Database where employee related all information can be captured, edited and added. | Add/Edit Employee, Login, Signup, Forget Password, Change Password, My Profile | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Master Listing | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Role Definition | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Employee Details Screen | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Internal Screen to View Performance Report | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Employee Leaves - Listing | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Employee Training | Add Training PDF | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Training Listing | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Employee Listing | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Detail Screen | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Leave Application module o CL (Half), PL (One), Close Leave (> 3 days) o Multiple approval | Apply Leave | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Applied Leaves | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Employee Leaves to Approve - By Manager | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Detail Screen | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Recruitment Requisition & Tracker | Add Vacancy | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Vacancy Listing | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | New Applications | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Application History | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Performance Appraisal | Employee Listing | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Send for Appraisal Request Form - 7 Roles along with Approved List | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | History | Umang/Sanjay | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Umang/Sanjay
4 | BD | Leads | Lead List | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Add Lead - Manual or Website | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Opportunity | Lead Conversion to Opportunity | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Opportunity Listing & Create New Opportunity Manually | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Organization | Organization Listing & Create Organization | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Contact | Contact Listing & Create New Contact | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Work Order | Work Order Listing & Create New Work Order | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Project | Project Listing & Create New Project | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Project details | Project details | Aman Darad | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
Aman Darad
|  | GRC Management Approval | GRC Management Approval | Aman Darad
5 | PM | Project Work Order Acceptance | Work Order Acceptance Request List | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Create Project | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Detail Screen | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Project Assignment to individual | Employee Listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Employee Assignment | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Employee Role Assignment | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Project Wise Status Tracking | All Project List along with their Status | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Uploading of documents project-wise | Document Upload & Listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Time Sheet/Time Log | Calender View | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Task Management | Task Listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Create Task | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Mudita/Satendra
6 | Accounts | Payment Recovery | Notifications for Due Date Payments | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Pending Invoice Listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Project Wise Expenses | Expenses listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Create Expense | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Pending Expenses | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Invoice Generation linked with Project Management Module | Create Invoice from Clients & Projects | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Invoice Listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Client addition, modification and editing | Client Listing | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Add New Client | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Call Log of all clients (Call/SMS/Email/Letters) | Manual Entry & Upload of All Logs | Mudita/Satendra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Mudita/Satendra
7 | IT | IT Asset Repository Management | Asset Listing | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Add Asset | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Asset Agreement PDF | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | IT Ticket Management | Create Ticket | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Ticket Listing | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Ticket Details Screen, Upload Attachments | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Purchase Order Generation for any IT or Admin Related Purchase | Purchase Order Listing | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Create New Order | Shyam/A N Mishra | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Shyam/A N Mishra
8 | Quality | Internal Audit Checklist and audits | Project Listing | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Audit history | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | New Audit | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Quality Formats Versioning and distribution | Upload Word, Issue to Employee, Employee Uploads Back to it. | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Umang
9 | Other Modules | Official Circulars | Listing | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | New Circular | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Knowledge Base Management/Best Practice Sharing | Lisitng | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | Document Management System | New Upload | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Folder Listing | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | File Listing | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  |  | Upload New Document - PDF, DOC, Excel, CSV, PPT Only | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Umang
10 | Others Required | Voice Note Recording for management for task assignment to any individual | Upload by Mic or choose Audio File Listing | Umang | Nitish/Priyanka/Pooja | Rajesh/Diksha/Pooja | Ajay
|  | GRC Management Approval | GRC Management Approval | Directors
11 |  | Handover | Delivery | All